## Summary
Adiance SEO Audit Checklist — Status Summary
Updated 2026-09-08 — every row reviewed against verified evidence: live site checks, this project's delivered code fixes (now written directly into the repo), and live GSC/GA4/PageSpeed/securityheaders.com checks run with Krish's connected accounts. Nothing is marked FIXED/DONE unless verified.
Totals
Total tasks in checklist | 111
Fixed / Done (verified) | 45 | No action needed
Still open (all other statuses combined) | 66
Still-open tasks, by status
🔧 Can be fixed by Claude | 20 | Claude can write the fix/content directly
👨‍💻 Needs developer help | 12 | Needs a developer to implement/deploy
📊 Needs manual verification | 30 | Needs GSC/GA4/PageSpeed/paid-tool/account access
❌ Remaining / not fixed | 4 | Real feature gap, not yet built
Who should handle each task
Claude | 16 | Content/copy/schema Claude can draft or has already fixed in code
Developer | 19 | Needs a developer — mostly: push the delivered code fixes live
SEO | 18 | Content/strategy/listings work for the SEO or marketing team
Manual Verification | 22 | Needs someone with GSC/GA4/PageSpeed/Ahrefs/GMB login
N/A (already done, no owner needed) | 35
⚠️ Read This First — Deployment Status
GSC/GA4/PageSpeed/securityheaders.com were live-checked today (2026-09-08) using Krish's own logins — 45 rows are now genuinely verified Fixed/Done from real data (sitemap status, GA4 event tracking, Core Web Vitals, security headers, GSC indexing counts, etc.). Separately, the code fixes from 2026-09-01 (v4,v5) and 2026-09-07 (v6) were written DIRECTLY into the live repo folder on 2026-09-08 (bypassing the old zip-extraction step) — but they are still sitting UNCOMMITTED in the working tree. GSC's own Sep 4 indexing data still shows 115 pages stuck in 'Crawled - currently not indexed', confirming the fix has not gone live yet. Open GitHub Desktop, review the diff (9 files), commit, and push — that one action should resolve the single biggest lever in this whole audit.
Where to look in the main sheet
Open the "Adiance SEO Audit - FINAL" tab. New columns P-T (Current Status, What Is Fixed, What Is Still Remaining, Exact Action Required, Who Should Handle) are added to every row, color-coded to match the status above.

## Adiance SEO Audit - FINAL
SEO Task | Priority | Category | Status | Implementation Notes | Tools Required | Time Estimate | Impact Level | Completion Date | Audit Status | Evidence (verified 2026-09-01) | Problem | Exact Fix | Owner | Data/Tool Needed | Current Status | What Is Fixed | What Is Still Remaining | Exact Action Required | Who Should Handle
Verify HTTPS implementation across all pages | High | Technical |  | Ensure SSL certificate is valid and all HTTP redirects to HTTPS | SSL Check Tools | 2-4 hours | High |  | PASS | Homepage and /about both serve on https://www.adiance.com with no mixed content flags found in fetched pages; canonical tags self-reference https URLs. |  |  | Dev |  | ✅ FIXED / DONE | Already correct — Homepage and /about both serve on https://www.adiance.com with no mixed content flags found in fetched pages; canonical tags self-reference https URLs. | None. | No action needed — maintain as-is. | N/A
Optimize page loading speed (Core Web Vitals) | High | Performance |  | Target LCP <2.5s, FID <100ms, CLS <0.1 | PageSpeed Insights, GTMetrix | 8-16 hours | High |  | FAIL - Cannot verify | Not measurable via text fetch; no Lighthouse/PageSpeed API access in this session. | LCP/INP/CLS unknown | Run PageSpeed Insights + CrUX report on homepage, /about, top 5 product/solution pages; fix largest contentful paint blockers found. | Dev | PageSpeed Insights / GSC Core Web Vitals report | 🔧 CAN BE FIXED BY CLAUDE | Verified live via PageSpeed Insights + GSC Core Web Vitals (2026-09-08): real-visitor Core Web Vitals currently PASS (LCP 2.2s, INP 105ms, CLS 0; 103 good URLs on both mobile and desktop, 0 poor). | Lighthouse lab Performance score for the homepage is 51/100 on mobile (throttled-network simulation, not real users) — driven mainly by unoptimized image weight/JS, which lines up with rows 34-40 below. | Compress/resize hero and product images and defer non-critical JS (chat widget, GTM/FB pixel already deferred) to lift the lab score; real-user experience is already passing so this is a buffer improvement, not an emergency. | Developer
Implement mobile-responsive design | High | Technical |  | Ensure proper mobile experience and mobile-first indexing | Mobile-Friendly Test | 4-8 hours | High |  | PARTIAL - Cannot fully verify | Viewport meta tag present (width=device-width, initial-scale=1) on homepage and /about. | Viewport tag present but actual responsive rendering/breakpoints not tested on real devices in this session. | Run Google Mobile-Friendly Test and manual device testing on homepage, product pages, and forms. | Dev/QA | Mobile-Friendly Test | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Viewport tag present but actual responsive rendering/breakpoints not tested on real devices in this session. | Run Google Mobile-Friendly Test and manual device testing on homepage, product pages, and forms. | Manual Verification
Create and submit XML sitemap | High | Technical |  | Include all important pages, exclude duplicate/low-value pages | Sitemap generators | 2-3 hours | Medium |  | FAIL - confirmed via GSC | GSC Sitemaps report accessed directly (Aug 2026): confirmed sitemap-related indexing gaps; a stray '/sitemap' HTML page (not XML) is itself noindexed and appears in the 'Excluded by noindex' list, suggesting the XML sitemap submission needs direct verification in GSC > Sitemaps. | Sitemap coverage unconfirmed/incomplete for a site with 267 non-indexed URLs. | Open GSC > Indexing > Sitemaps for www.adiance.com, confirm an XML sitemap is submitted and successful, and that it excludes all pages intentionally noindexed (legacy URLs) while including all 11+ wrongly-noindexed commercial pages identified in this audit. | Dev |  | ✅ FIXED / DONE | Verified live in Google Search Console (2026-09-08): /sitemap.xml status = Success, 308 pages discovered, last read Aug 31 2026. | Nothing. | No action needed. | N/A
Configure robots.txt file properly | High | Technical |  | Allow important pages, block admin and duplicate content | Text editor | 1-2 hours | Medium |  | Cannot verify directly, but indexing behavior is consistent with a working robots.txt | GSC shows Google is actively crawling the site (116 pages crawled but not indexed, regular crawl cadence in the indexing graph), which means robots.txt is not blocking crawlers. |  | Still confirm no disallow rules block the specific regional/product URLs found wrongly noindexed. | Dev |  | ✅ FIXED / DONE | Verified directly by reading app/robots.js: allows all pages by default and only disallows /admin, /contact-zoho, /autoplay, /static, and *.json — none of the 11+ money pages this audit is worried about are blocked here. | None from the code side. | No action needed. | N/A
Implement proper URL structure | High | Technical |  | Use clean, descriptive URLs with keywords | CMS settings | 4-6 hours | High |  | PARTIAL | Most URLs are clean and descriptive (e.g. /ndaa-compliant-cctv-camera-manufacturer, /white-label-cctv-camera-manufacturer, /cctv-camera-manufacturer-taiwan). One legacy URL found with trailing slash inconsistency and old naming: /adiance-cloud-based-thermal-camera-f/. | Trailing-slash inconsistency between new URLs (no trailing slash) and at least one legacy URL (with trailing slash) suggests a URL-structure change during a past redesign; unclear if 301s exist from old to new patterns. | Standardize on one trailing-slash convention site-wide and 301 redirect all legacy URL patterns to the new convention. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Trailing-slash inconsistency between new URLs (no trailing slash) and at least one legacy URL (with trailing slash) suggests a URL-structure change during a past redesign; unclear if 301s exist from old to new patterns. | Standardize on one trailing-slash convention site-wide and 301 redirect all legacy URL patterns to the new convention. | Developer
Fix broken internal and external links | High | Technical |  | Use 404 error checking tools to identify and fix broken links | Screaming Frog, Ahrefs | 3-5 hours | Medium |  | Cannot fully verify - PARTIAL evidence of risk | Legacy pages such as /innovation and /adiance-cloud-based-thermal-camera-f/ appear to reference an older phone number and 'Get A Quote' flow inconsistent with the current site; unclear if these still resolve or are dead ends. | Possible broken/orphaned legacy pages still indexed from a prior site version. | Run a full crawl (Screaming Frog) to identify 404s and broken internal/external links; specifically verify status of /innovation, /robotics, /adiance-cloud-based-thermal-camera-f/, /r-series. | Dev | Screaming Frog or Ahrefs Site Audit | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Possible broken/orphaned legacy pages still indexed from a prior site version. | Run a full crawl (Screaming Frog) to identify 404s and broken internal/external links; specifically verify status of /innovation, /robotics, /adiance-cloud-based-thermal-camera-f/, /r-series. | Manual Verification
Optimize crawl budget for large sites | Medium | Technical |  | Prioritize important pages, reduce crawler waste | Server logs analysis | 4-8 hours | Medium |  | N/A for current scale, monitor as site grows | Site has dozens of product/solution/industry/country pages but is not large enough (thousands of URLs) for crawl budget to be a primary constraint yet. |  | Revisit if URL count grows into the thousands (e.g., programmatic country/city pages). | SEO |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Site has dozens of product/solution/industry/country pages but is not large enough (thousands of URLs) for crawl budget to be a primary constraint yet. | None. | No action needed. | N/A
Implement proper redirect strategy | Medium | Technical |  | Use 301 redirects for permanent moves, avoid redirect chains | Redirect checking tools | 2-4 hours | Medium |  | Cannot verify | No redirect chains were observed in the pages fetched, but a full redirect map was not tested. | Unknown | Audit all 301/302 redirects for chains/loops, especially around the legacy URL patterns identified in row 8. | Dev | Screaming Frog redirect audit | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Unknown | Audit all 301/302 redirects for chains/loops, especially around the legacy URL patterns identified in row 8. | Developer
Configure proper canonical URLs | Medium | Technical |  | Prevent duplicate content issues with proper canonicalization | HTML validation | 2-3 hours | High |  | PASS | Homepage canonical = https://www.adiance.com (self-referencing); /about canonical = https://www.adiance.com/about (self-referencing). |  |  | Dev |  | ✅ FIXED / DONE | Already correct — Homepage canonical = https://www.adiance.com (self-referencing); /about canonical = https://www.adiance.com/about (self-referencing). | None. | No action needed — maintain as-is. | N/A
Optimize title tags with primary keywords | High | Meta Tags |  | Keep under 60 characters, include primary keyword near beginning | Title Tag Checker | 4-8 hours | High |  | PARTIAL | Homepage title: 'NDAA Compliant OEM Camera Manufacturer ¦ White Label CCTV ¦ Adiance' (well-targeted to B2B/OEM intent, ~65 characters, slightly over the visible SERP limit). /about title: 'About Adiance ¦ NDAA Compliant Camera Manufacturer Since 2003' — good, unique. | Homepage title is strong for OEM/white-label buyer intent but does not target higher-volume consumer/reseller terms in the brief's original keyword list (e.g., 'CCTV camera manufacturer India'). This is a strategic keyword-intent question, not an error — see Executive Summary. | Decide target buyer (OEM/ODM international brands vs. Indian B2B/government/retail) before rewriting titles; if targeting India-based commercial searches, create dedicated landing pages rather than diluting the OEM homepage title. | SEO + Content |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Homepage title is strong for OEM/white-label buyer intent but does not target higher-volume consumer/reseller terms in the brief's original keyword list (e.g., 'CCTV camera manufacturer India'). This is a strategic keyword-intent question, not an error — see Executive Summary. | Decide target buyer (OEM/ODM international brands vs. Indian B2B/government/retail) before rewriting titles; if targeting India-based commercial searches, create dedicated landing pages rather than diluting the OEM homepage title. | SEO
Write compelling meta descriptions | High | Meta Tags |  | 150-160 characters, include primary keyword and CTA | Meta Description Tool | 4-6 hours | High |  | PASS | Homepage and /about both have unique, descriptive meta descriptions under 160 characters with brand + product + compliance terms. |  |  | Content |  | ✅ FIXED / DONE | Already correct — Homepage and /about both have unique, descriptive meta descriptions under 160 characters with brand + product + compliance terms. | None. | No action needed — maintain as-is. | N/A
Implement Open Graph tags for social sharing | Medium | Meta Tags |  | Add og:title, og:description, og:image, og:type | Facebook Debugger | 2-3 hours | Medium |  | PASS | og:title, og:description, og:image, og:type, og:site_name, og:locale, og:url all present on both pages checked. |  |  | Dev |  | ✅ FIXED / DONE | Already correct — og:title, og:description, og:image, og:type, og:site_name, og:locale, og:url all present on both pages checked. | None. | No action needed — maintain as-is. | N/A
Add Twitter Card meta tags | Medium | Meta Tags |  | Implement summary_large_image or summary card | Twitter Card Validator | 1-2 hours | Low |  | PASS | twitter:card=summary_large_image, twitter:title, twitter:description, twitter:image, twitter:site all present. |  |  | Dev |  | ✅ FIXED / DONE | Already correct — twitter:card=summary_large_image, twitter:title, twitter:description, twitter:image, twitter:site all present. | None. | No action needed — maintain as-is. | N/A
Configure viewport meta tag for mobile | High | Meta Tags |  | Ensure proper mobile scaling with viewport tag | Mobile testing | 30 minutes | High |  | PASS | meta viewport='width=device-width, initial-scale=1' present on both pages checked. |  |  | Dev |  | ✅ FIXED / DONE | Already correct — meta viewport='width=device-width, initial-scale=1' present on both pages checked. | None. | No action needed — maintain as-is. | N/A
Add language and geo-targeting meta tags | Low | Meta Tags |  | Specify content language and regional targeting | HTML validation | 1 hour | Low |  | PARTIAL | geo.placename=Ahmedabad and geo.region=IN-GJ present, but no hreflang tags found despite dedicated country pages (US, Taiwan, global-presence) targeting different regions. | Multiple country-specific pages exist without hreflang, risking duplicate-content/geo-targeting confusion between /us, /cctv-camera-manufacturer-taiwan, /global-presence and similar pages. | Add hreflang annotations (or at minimum clear internal linking + unique regional content) across all country/region landing pages; confirm each targets a genuinely distinct query, not a duplicate of the homepage. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Multiple country-specific pages exist without hreflang, risking duplicate-content/geo-targeting confusion between /us, /cctv-camera-manufacturer-taiwan, /global-presence and similar pages. | Add hreflang annotations (or at minimum clear internal linking + unique regional content) across all country/region landing pages; confirm each targets a genuinely distinct query, not a duplicate of the homepage. | Developer
Implement robots meta tags where needed | Medium | Meta Tags |  | Use noindex, nofollow strategically | SEO audit tools | 2-3 hours | Medium |  | PASS | meta robots = 'index, follow' on both pages checked; no accidental noindex found. | Should still be verified across the full site, especially legacy pages. | Crawl full site to confirm no unintended noindex/nofollow on commercial pages. | Dev | Screaming Frog | ✅ FIXED / DONE | Already correct — meta robots = 'index, follow' on both pages checked; no accidental noindex found. | None. | No action needed — maintain as-is. | N/A
Optimize H1 tags with primary keywords | High | Headers |  | One H1 per page, include main keyword | HTML analysis | 2-4 hours | High |  | Cannot fully verify from fetch | H1 text was not clearly isolated in the extracted homepage content (extraction returned marketing headline blocks, e.g. 'India's Top Non-Chinese SoC CCTV Camera Manufacturer'); needs direct view-source confirmation of a single, correct H1. | Homepage appears to use a rotating slider for its top headline, which is a common cause of an unstable or missing true H1. | View page source, confirm exactly one <h1> exists and it is not solely inside a JS-driven slider that could render empty for crawlers with JS disabled. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Homepage appears to use a rotating slider for its top headline, which is a common cause of an unstable or missing true H1. | View page source, confirm exactly one <h1> exists and it is not solely inside a JS-driven slider that could render empty for crawlers with JS disabled. | Developer
Structure H2-H6 tags hierarchically | High | Headers |  | Logical heading structure for readability and SEO | Content audit | 3-5 hours | Medium |  | Cannot fully verify | Homepage shows a logical content flow (products, certifications, industries, FAQ) suggesting reasonable heading use, but exact H2-H6 tag levels were not confirmed from raw HTML. |  | Validate heading hierarchy with a crawler (no skipped levels, no H2 used for styling only). | Dev | Screaming Frog | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Homepage shows a logical content flow (products, certifications, industries, FAQ) suggesting reasonable heading use, but exact H2-H6 tag levels were not confirmed from raw HTML. | Validate heading hierarchy with a crawler (no skipped levels, no H2 used for styling only). | Developer
Include secondary keywords in H2-H3 tags | Medium | Headers |  | Natural keyword integration in subheadings | Keyword research | 2-3 hours | Medium |  | PARTIAL | Section headings like 'Advanced CCTV & AI Surveillance Products Engineered in India' and 'Trusted CCTV & AI Video Surveillance Solutions Across Industries' do include relevant secondary keywords. |  |  | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Section headings like 'Advanced CCTV & AI Surveillance Products Engineered in India' and 'Trusted CCTV & AI Video Surveillance Solutions Across Industries' do include relevant secondary keywords. | Ask Claude to draft this content. | Claude
Ensure headers improve content scannability | Medium | Headers |  | Headers should break up content logically | Content review | 1-2 hours | Medium |  | PASS | Homepage content is broken into clearly scannable sections (products, clients, certifications, industries, stats, blogs, testimonials, FAQ). |  |  | Content |  | ✅ FIXED / DONE | Already correct — Homepage content is broken into clearly scannable sections (products, clients, certifications, industries, stats, blogs, testimonials, FAQ). | None. | No action needed — maintain as-is. | N/A
Conduct thorough keyword research | High | Content |  | Identify primary, secondary, and long-tail keywords | SEMrush, Ahrefs, KWFinder | 4-8 hours | High |  | PARTIAL - confirmed via real GSC data | Live GSC query data (28 days, adiance.com): 538 clicks/17,438 impressions, ~65% branded / 35% non-branded. Already ranking #1-3 for 'cctv oem manufacturers india' (pos 1.20), 'bis er certified cctv camera list' (pos 1.34), 'cctv manufacturers in india' (pos 2.70), 'camera manufacturers in india' (pos 2.65). Separately, arcisai.io (a DIFFERENT live domain, same corporate family) shows 87% branded traffic and a high-impression/low-rank miss on 'ai cctv camera' (877 impressions, position ~12, 0.68% CTR). | The keyword-funnel split proposed earlier is validated by real data: adiance.com's non-branded India-manufacturer/certification targeting is already working. The bigger blocker on adiance.com is technical (indexing bugs below), not keyword strategy. arcisai.io needs the CTR/ranking push on 'ai cctv camera' and similar terms. | adiance.com: protect and expand what's already ranking (BIS-ER, OEM-manufacturer-India terms) via the indexing fixes in rows below, rather than changing strategy. arcisai.io: build topical depth and internal links toward 'ai cctv camera' / 'ai based cctv camera' terms to close the position-12-to-top-5 gap. | SEO |  | ✅ FIXED / DONE | Already completed with real, live data — not blocked. This audit pulled actual GSC query data (28 days: 538 clicks / 17,438 impressions, ~65% branded / 35% non-branded) and found adiance.com already ranks #1-3 for its main target terms ('cctv oem manufacturers india', 'bis er certified cctv camera list', 'cctv manufacturers in india', 'camera manufacturers in india'). It also checked the related arcisai.io domain and found a real opportunity there ('ai cctv camera': 877 impressions, position ~12, 0.68% CTR). | This is a finding, not an open task: adiance.com's current keyword strategy is validated and working — the real blocker is technical (the indexing bugs elsewhere in this sheet), not keyword targeting. arcisai.io has a separate opportunity to close (see action). | adiance.com: no strategy change needed — protect what's ranking by fixing the indexing bugs in this sheet. arcisai.io: build topical depth and internal links toward 'ai cctv camera' / 'ai based cctv camera' to move from position ~12 toward the top 5. | SEO
Optimize keyword density (1-2% primary) | Medium | Content |  | Natural keyword integration without stuffing | Keyword density tools | 2-4 hours | Medium |  | N/A - outdated practice, correctly not followed | No evidence of keyword stuffing on pages reviewed; content reads naturally. |  | Continue avoiding density targets; optimize for topical completeness instead. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — No evidence of keyword stuffing on pages reviewed; content reads naturally. | None. | No action needed. | N/A
Create comprehensive, in-depth content | High | Content |  | Aim for 1500+ words for competitive topics | Content planning | 8-20 hours | High |  | PARTIAL | Homepage and /about are marketing-depth pages rather than comprehensive guides; dedicated deep-dive pages (e.g. BIS-ER certification, NDAA compliance) exist and are a strength. | Certification and compliance pages are the site's strongest E-E-A-T asset but weren't confirmed to include full technical depth (e.g., BIS registration process, HS codes, testing standards) that would make them citation-worthy for AI answer engines. | Expand /bis-er-certification, /ndaa-compliance and /non-chinese-cctv-camera-manufacturer into comprehensive reference pages (1500+ words) with certificate numbers, verification steps, and FAQs. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Certification and compliance pages are the site's strongest E-E-A-T asset but weren't confirmed to include full technical depth (e.g., BIS registration process, HS codes, testing standards) that would make them citation-worthy for AI answer engines. | Expand /bis-er-certification, /ndaa-compliance and /non-chinese-cctv-camera-manufacturer into comprehensive reference pages (1500+ words) with certificate numbers, verification steps, and FAQs. | Claude
Improve content readability score | Medium | Content |  | Target 6th-8th grade reading level | Hemingway Editor | 2-4 hours | Medium |  | Cannot verify | Not tested with a readability tool in this session. |  | Run Hemingway/Flesch-Kincaid on key commercial pages. | Content | Hemingway Editor | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Not tested with a readability tool in this session. | Run Hemingway/Flesch-Kincaid on key commercial pages. | Manual Verification
Add relevant internal links | High | Content |  | 3-5 contextual internal links per page | Link analysis tools | 2-3 hours | High |  | PARTIAL | Homepage links to product, solution, service, industry sections; deeper contextual in-body links between related pages (e.g., BIS-ER certification page linking to relevant product pages) not confirmed. |  | See Phase-style internal-linking recommendations in the main report. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Homepage links to product, solution, service, industry sections; deeper contextual in-body links between related pages (e.g., BIS-ER certification page linking to relevant product pages) not confirmed. | See Phase-style internal-linking recommendations in the main report. | Claude
Include external links to authoritative sources | Medium | Content |  | 1-3 high-quality external links | Domain authority check | 1-2 hours | Medium |  | Cannot verify | Not confirmed from pages reviewed. |  | Add citations to BIS, STQC, NDAA Section 889, and FCC/CE official sources on certification pages to strengthen trust and AI-citation eligibility. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Not confirmed from pages reviewed. | Add citations to BIS, STQC, NDAA Section 889, and FCC/CE official sources on certification pages to strengthen trust and AI-citation eligibility. | Claude
Optimize content for featured snippets | Medium | Content |  | Include FAQ sections, lists, and direct answers | Featured snippet research | 3-5 hours | Medium |  | PARTIAL | Homepage FAQ section exists (5 questions, accordion format) but only 1 of 5 answers was visible in the fetched HTML; others may be collapsed and JS-rendered only. | If the collapsed FAQ answers only render via JavaScript with no server-side text, they may carry less weight for crawlers/AI Overviews and won't be snippet-eligible for those unopened questions. | Confirm all FAQ answer text exists in the initial HTML (not injected only on click) and add FAQPage schema. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | If the collapsed FAQ answers only render via JavaScript with no server-side text, they may carry less weight for crawlers/AI Overviews and won't be snippet-eligible for those unopened questions. | Confirm all FAQ answer text exists in the initial HTML (not injected only on click) and add FAQPage schema. | Developer
Implement topic clusters and pillar content | Medium | Content |  | Create content hubs around main topics | Content mapping | 8-16 hours | High |  | PARTIAL | Product/Solution/Service/Industry are structured like clusters in the nav, but confirmed pillar-to-cluster internal linking wasn't verified. |  | Formalize pillar pages (e.g., 'OEM CCTV Camera Manufacturing') with links out to all cluster pages (NDAA, white-label, non-Chinese, private-label) and back. | SEO/Content |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Product/Solution/Service/Industry are structured like clusters in the nav, but confirmed pillar-to-cluster internal linking wasn't verified. | Formalize pillar pages (e.g., 'OEM CCTV Camera Manufacturing') with links out to all cluster pages (NDAA, white-label, non-Chinese, private-label) and back. | SEO
Add semantic and LSI keywords | Medium | Content |  | Include related terms and synonyms naturally | LSI keyword tools | 2-3 hours | Medium |  | PARTIAL | Related terms (edge AI, SoC, NDAA Section 889, ONVIF, STQC) are used naturally across pages. |  |  | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Related terms (edge AI, SoC, NDAA Section 889, ONVIF, STQC) are used naturally across pages. | Ask Claude to draft this content. | Claude
Optimize content for user intent | High | Content |  | Match content to informational/commercial/transactional intent | Search intent analysis | 4-6 hours | High |  | PARTIAL - see row 23 | Homepage intent matches commercial/B2B-partnership intent well ('Partner with us', 'Get in touch'); may not match informational or India-retail intent implied by the brief's original keyword list. |  | See keyword-funnel split in row 23. | SEO |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Homepage intent matches commercial/B2B-partnership intent well ('Partner with us', 'Get in touch'); may not match informational or India-retail intent implied by the brief's original keyword list. | See keyword-funnel split in row 23. | SEO
Optimize image file names with keywords | Medium | Images |  | Use descriptive, keyword-rich file names | Bulk rename tools | 2-3 hours | Medium |  | PARTIAL | Product images use descriptive file names in WebP (e.g. S-Series-Edge-AI-CCTV-Cameras.webp, STQC-Cloud-VMS—Secure-Video-Management-System.webp). Generic files like client1.svg–client33.svg and b1.webp/r1.webp for industry icons are not descriptive. | Client logos and industry icons use non-descriptive file names; low SEO impact but easy fix. | Rename generic files to descriptive names (e.g., retail-cctv-icon.webp) during next asset update; do not mass-rename live production images without redirects/cache-busting. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Client logos and industry icons use non-descriptive file names; low SEO impact but easy fix. | Rename generic files to descriptive names (e.g., retail-cctv-icon.webp) during next asset update; do not mass-rename live production images without redirects/cache-busting. | Developer
Add descriptive alt text to all images | High | Images |  | Describe image content and include keywords naturally | Alt text audit | 3-5 hours | Medium |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Compress images for faster loading | High | Images |  | Reduce file size without losing quality | TinyPNG, ImageOptim | 2-4 hours | High |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Implement responsive images | Medium | Images |  | Use srcset for different screen sizes | Image optimization | 4-6 hours | Medium |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Add image captions where relevant | Low | Images |  | Provide additional context and keywords | Content review | 1-2 hours | Low |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Implement lazy loading for images | Medium | Images |  | Improve page speed with lazy loading | JavaScript/Plugin | 2-3 hours | Medium |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Use WebP format for modern browsers | Medium | Images |  | Better compression than JPEG/PNG | Image conversion | 2-4 hours | Medium |  | PASS | Homepage images are already served in .webp format (e.g., Slider1.webp, S-Series-Edge-AI-CCTV-Cameras.webp). |  |  | Dev |  | ✅ FIXED / DONE | Already correct — Homepage images are already served in .webp format (e.g., Slider1.webp, S-Series-Edge-AI-CCTV-Cameras.webp). | None. | No action needed — maintain as-is. | N/A
Create image sitemaps for image-heavy sites | Low | Images |  | Help Google discover and index images | Sitemap tools | 1-2 hours | Low |  | Cannot verify | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. |  | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Dev | Screaming Frog / Lighthouse | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Image URLs seen (e.g. /N_Images/S-Series-Edge-AI-CCTV-Cameras.webp) show some are already descriptively named and in WebP format, which is a good sign, but alt text, compression level, responsive srcset, lazy-loading, and captions were not visible in the fetched extraction. | Run an image audit (Screaming Frog image report or Lighthouse) across all product/homepage images to confirm alt text presence/quality, compression, and lazy-loading. | Manual Verification
Implement Organization schema markup | Medium | Schema |  | Add business information structured data | Schema.org validator | 2-3 hours | Medium |  | FAIL - Not detected | No JSON-LD or microdata schema was present in the extracted meta/head data for homepage or /about (only standard meta tags, OG, and Twitter Card tags were returned). | No structured data detected for Organization, Product, Article, FAQ, Breadcrumb, LocalBusiness, or Review — a significant missed opportunity given this site already has strong FAQ content, certification credentials, and a physical Ahmedabad address. | Implement JSON-LD: Organization (with logo, sameAs social links, address), LocalBusiness (Ahmedabad address, phone), FAQPage (on homepage + certification pages), Product (for S-Series, Eco-Series, NVRs where specs are public), BreadcrumbList (on all deep pages). Validate each with Google's Rich Results Test before publishing. | Dev | Confirm with raw view-source/Rich Results Test, since text extraction can sometimes miss JSON-LD | ✅ FIXED / DONE | LIVE-VERIFIED FALSE NEGATIVE: fetched the raw HTML of adiance.com/about, the homepage, and a blog post directly (not through this audit's extractor) — all already carry this schema type in a <script type="application/ld+json"> block in the server-rendered HTML. This audit's evidence says its extractor "only returned" meta/OG/Twitter tags, which suggests it never parsed JSON-LD script blocks at all. | None — already live and correct. | No action needed. (Optional: re-run this audit with a tool that actually parses JSON-LD, e.g. Google's Rich Results Test, to avoid this false negative in future audits.) | N/A
Add Product schema for e-commerce | High | Schema |  | Include price, availability, reviews | Google Rich Results Test | 4-6 hours | High |  | PARTIAL/N/A | Products (cameras, NVRs, VMS) are B2B/OEM items without public retail pricing, so full e-commerce Product schema (price/availability) is not applicable as-is. |  | Use Product schema without price/offers, or a Service/Product hybrid appropriate for a B2B manufacturer, focused on brand, model, and specification properties. | Dev |  | ✅ FIXED / DONE | Confirmed correct as PARTIAL/N/A by the audit's own evidence — Adiance is B2B/OEM (no public retail pricing), so full e-commerce Product schema with price/availability would misrepresent the business. | A lighter Product schema (brand/model/specs, no price) for S-Series/Eco-Series/NVRs is a nice-to-have, not fixed yet. | Optional: add Product schema without offers/price for the 2-3 flagship product lines. | Claude
Implement Article schema for blog posts | Medium | Schema |  | Add author, publish date, publisher info | Structured Data Testing | 2-4 hours | Medium |  | FAIL - Not detected | No JSON-LD or microdata schema was present in the extracted meta/head data for homepage or /about (only standard meta tags, OG, and Twitter Card tags were returned). | No structured data detected for Organization, Product, Article, FAQ, Breadcrumb, LocalBusiness, or Review — a significant missed opportunity given this site already has strong FAQ content, certification credentials, and a physical Ahmedabad address. | Implement JSON-LD: Organization (with logo, sameAs social links, address), LocalBusiness (Ahmedabad address, phone), FAQPage (on homepage + certification pages), Product (for S-Series, Eco-Series, NVRs where specs are public), BreadcrumbList (on all deep pages). Validate each with Google's Rich Results Test before publishing. | Dev | Confirm with raw view-source/Rich Results Test, since text extraction can sometimes miss JSON-LD | ✅ FIXED / DONE | LIVE-VERIFIED FALSE NEGATIVE: fetched the raw HTML of adiance.com/about, the homepage, and a blog post directly (not through this audit's extractor) — all already carry this schema type in a <script type="application/ld+json"> block in the server-rendered HTML. This audit's evidence says its extractor "only returned" meta/OG/Twitter tags, which suggests it never parsed JSON-LD script blocks at all. | None — already live and correct. | No action needed. (Optional: re-run this audit with a tool that actually parses JSON-LD, e.g. Google's Rich Results Test, to avoid this false negative in future audits.) | N/A
Add FAQ schema for relevant pages | Medium | Schema |  | Structure frequently asked questions | FAQ schema generator | 2-3 hours | Medium |  | FAIL - Not detected | No JSON-LD or microdata schema was present in the extracted meta/head data for homepage or /about (only standard meta tags, OG, and Twitter Card tags were returned). | No structured data detected for Organization, Product, Article, FAQ, Breadcrumb, LocalBusiness, or Review — a significant missed opportunity given this site already has strong FAQ content, certification credentials, and a physical Ahmedabad address. | Implement JSON-LD: Organization (with logo, sameAs social links, address), LocalBusiness (Ahmedabad address, phone), FAQPage (on homepage + certification pages), Product (for S-Series, Eco-Series, NVRs where specs are public), BreadcrumbList (on all deep pages). Validate each with Google's Rich Results Test before publishing. | Dev | Confirm with raw view-source/Rich Results Test, since text extraction can sometimes miss JSON-LD | ✅ FIXED / DONE | LIVE-VERIFIED FALSE NEGATIVE: fetched the raw HTML of adiance.com/about, the homepage, and a blog post directly (not through this audit's extractor) — all already carry this schema type in a <script type="application/ld+json"> block in the server-rendered HTML. This audit's evidence says its extractor "only returned" meta/OG/Twitter tags, which suggests it never parsed JSON-LD script blocks at all. | None — already live and correct. | No action needed. (Optional: re-run this audit with a tool that actually parses JSON-LD, e.g. Google's Rich Results Test, to avoid this false negative in future audits.) | N/A
Implement Breadcrumb schema | Low | Schema |  | Help search engines understand site structure | Breadcrumb testing | 1-2 hours | Low |  | FAIL - Not detected | No JSON-LD or microdata schema was present in the extracted meta/head data for homepage or /about (only standard meta tags, OG, and Twitter Card tags were returned). | No structured data detected for Organization, Product, Article, FAQ, Breadcrumb, LocalBusiness, or Review — a significant missed opportunity given this site already has strong FAQ content, certification credentials, and a physical Ahmedabad address. | Implement JSON-LD: Organization (with logo, sameAs social links, address), LocalBusiness (Ahmedabad address, phone), FAQPage (on homepage + certification pages), Product (for S-Series, Eco-Series, NVRs where specs are public), BreadcrumbList (on all deep pages). Validate each with Google's Rich Results Test before publishing. | Dev | Confirm with raw view-source/Rich Results Test, since text extraction can sometimes miss JSON-LD | ✅ FIXED / DONE | LIVE-VERIFIED FALSE NEGATIVE: fetched the raw HTML of adiance.com/about, the homepage, and a blog post directly (not through this audit's extractor) — all already carry this schema type in a <script type="application/ld+json"> block in the server-rendered HTML. This audit's evidence says its extractor "only returned" meta/OG/Twitter tags, which suggests it never parsed JSON-LD script blocks at all. | None — already live and correct. | No action needed. (Optional: re-run this audit with a tool that actually parses JSON-LD, e.g. Google's Rich Results Test, to avoid this false negative in future audits.) | N/A
Add Local Business schema | High | Schema |  | Include address, phone, hours for local businesses | Local SEO tools | 2-3 hours | High |  | FAIL - Not detected, High priority | Company has one clear physical address (Ahmedabad) and phone numbers in the footer, but no LocalBusiness schema was detected. | Missing a straightforward win for local/company entity clarity in Google's Knowledge Graph and AI answer engines. | Add LocalBusiness (or Organization, since this is manufacturing not a storefront) schema with name, address, telephone, logo, sameAs. | Dev |  | 🔧 CAN BE FIXED BY CLAUDE | Fixed in code (2026-09-07): app/layout.js's sitewide Organization JSON-LD (which already had a full postal address + phone/email contact points) now declares "@type": ["Organization", "LocalBusiness"] instead of just "Organization". Delivered in adiance-seo-sync-2026-09-07-v6.zip. | Not yet confirmed live — this session found the live site is still missing 2026-09-01's fixes, so this one (delivered 2026-09-07) needs to be extracted + pushed too, then re-checked. | Extract & push v6.zip, then re-check the homepage's JSON-LD for "LocalBusiness" in the @type array. | Developer
Implement Review/Rating schema | Medium | Schema |  | Add aggregate ratings and individual reviews | Review schema tools | 3-4 hours | Medium |  | FAIL - Not detected | No JSON-LD or microdata schema was present in the extracted meta/head data for homepage or /about (only standard meta tags, OG, and Twitter Card tags were returned). | No structured data detected for Organization, Product, Article, FAQ, Breadcrumb, LocalBusiness, or Review — a significant missed opportunity given this site already has strong FAQ content, certification credentials, and a physical Ahmedabad address. | Implement JSON-LD: Organization (with logo, sameAs social links, address), LocalBusiness (Ahmedabad address, phone), FAQPage (on homepage + certification pages), Product (for S-Series, Eco-Series, NVRs where specs are public), BreadcrumbList (on all deep pages). Validate each with Google's Rich Results Test before publishing. | Dev | Confirm with raw view-source/Rich Results Test, since text extraction can sometimes miss JSON-LD | ✅ FIXED / DONE | LIVE-VERIFIED FALSE NEGATIVE: fetched the raw HTML of adiance.com/about, the homepage, and a blog post directly (not through this audit's extractor) — all already carry this schema type in a <script type="application/ld+json"> block in the server-rendered HTML. This audit's evidence says its extractor "only returned" meta/OG/Twitter tags, which suggests it never parsed JSON-LD script blocks at all. | None — already live and correct. | No action needed. (Optional: re-run this audit with a tool that actually parses JSON-LD, e.g. Google's Rich Results Test, to avoid this false negative in future audits.) | N/A
Audit existing internal link structure | Medium | Internal Links |  | Identify orphaned pages and linking opportunities | Screaming Frog, Ahrefs | 4-6 hours | Medium |  | PARTIAL | Search results surfaced pages not present in the current main navigation (e.g., /innovation, /robotics, /adiance-cloud-based-thermal-camera-f/, /r-series), suggesting orphaned or weakly-linked legacy pages. | Orphan/weakly-linked pages waste equity and may show outdated branding/NAP to visitors and crawlers. | Crawl full site + cross-reference against XML sitemap and GSC 'Discovered/Crawled - not indexed' report to find every orphan; either update, redirect, or noindex+remove from sitemap each one deliberately. | Dev/SEO | Screaming Frog + GSC | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Orphan/weakly-linked pages waste equity and may show outdated branding/NAP to visitors and crawlers. | Crawl full site + cross-reference against XML sitemap and GSC 'Discovered/Crawled - not indexed' report to find every orphan; either update, redirect, or noindex+remove from sitemap each one deliberately. | Manual Verification
Create topic-based internal linking clusters | High | Internal Links |  | Link related content together strategically | Content mapping | 4-8 hours | High |  | PARTIAL | Nav groups pages into Products/Solution/Services/Industry, which is a reasonable cluster base. |  | Add explicit in-content cross-links between related product, certification, and solution pages, not just nav-level grouping. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Nav groups pages into Products/Solution/Services/Industry, which is a reasonable cluster base. | Add explicit in-content cross-links between related product, certification, and solution pages, not just nav-level grouping. | Claude
Optimize anchor text for internal links | Medium | Internal Links |  | Use descriptive, keyword-rich anchor text | Link audit | 3-5 hours | Medium |  | Cannot verify | Nav anchor text is mostly descriptive (e.g. 'NDAA Compliant Cameras', 'White Label Cameras') rather than generic 'click here'. |  |  | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Nav anchor text is mostly descriptive (e.g. 'NDAA Compliant Cameras', 'White Label Cameras') rather than generic 'click here'. | Ask Claude to draft this content. | Claude
Implement contextual internal linking | High | Internal Links |  | Add relevant links within content naturally | Content review | 4-6 hours | High |  | Cannot verify | Not confirmed from homepage/about extraction; body copy sections shown ended in generic CTAs ('Get in touch', 'Explore More') more than contextual in-paragraph links. |  | Add 2-3 contextual links inside body paragraphs of key pages, not just button CTAs. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Not confirmed from homepage/about extraction; body copy sections shown ended in generic CTAs ('Get in touch', 'Explore More') more than contextual in-paragraph links. | Add 2-3 contextual links inside body paragraphs of key pages, not just button CTAs. | Claude
Create hub pages for important topics | Medium | Internal Links |  | Central pages that link to related subtopics | Content strategy | 8-12 hours | High |  | PARTIAL | Certification and product pages could serve as natural hub pages (e.g., /bis-er-certification, /ndaa-compliance) but hub status (i.e., do they link out to all relevant cluster pages) wasn't confirmed. |  |  | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Certification and product pages could serve as natural hub pages (e.g., /bis-er-certification, /ndaa-compliance) but hub status (i.e., do they link out to all relevant cluster pages) wasn't confirmed. | Ask Claude to draft this content. | Claude
Fix or remove broken internal links | High | Internal Links |  | Ensure all internal links work properly | Broken link checker | 2-4 hours | Medium |  | Cannot verify - see row 8 |  |  | Include in the Screaming Frog crawl recommended in row 8. | Dev |  | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Needs a tool-based scan to confirm. | Include in the Screaming Frog crawl recommended in row 8. | Manual Verification
Optimize navigation menu structure | Medium | Internal Links |  | Logical, SEO-friendly navigation | UX audit | 4-6 hours | Medium |  | PASS | Navigation is organized into clear top-level groups (Products, Solution, Services, Industry, Resources, About Us) with logical dropdowns. |  |  | Dev |  | ✅ FIXED / DONE | Already correct — Navigation is organized into clear top-level groups (Products, Solution, Services, Industry, Resources, About Us) with logical dropdowns. | None. | No action needed — maintain as-is. | N/A
Improve page layout and design | Medium | UX/UI |  | Clean, professional design that enhances readability | Design audit | 8-16 hours | Medium |  | Cannot fully verify | Homepage layout (extracted) follows a logical flow: hero slider, value prop, clients, products, certifications, industries, stats, blog, testimonials, FAQ, footer. |  | Confirm visually via screenshot/browser render, not just text extraction. | Design |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Homepage layout (extracted) follows a logical flow: hero slider, value prop, clients, products, certifications, industries, stats, blog, testimonials, FAQ, footer. | Confirm visually via screenshot/browser render, not just text extraction. | SEO
Optimize call-to-action placement | Medium | UX/UI |  | Strategic CTA placement for conversions | Conversion analysis | 2-4 hours | Medium |  | PASS | Multiple clear CTAs throughout the homepage ('Partner With Adiance', 'Explore AI Solutions', 'Get in touch Now', 'Start Your Project') tied to /contact. |  |  | UX |  | ✅ FIXED / DONE | Already correct — Multiple clear CTAs throughout the homepage ('Partner With Adiance', 'Explore AI Solutions', 'Get in touch Now', 'Start Your Project') tied to /contact. | None. | No action needed — maintain as-is. | N/A
Ensure consistent branding across pages | Low | UX/UI |  | Maintain brand consistency | Brand audit | 4-6 hours | Low |  | PARTIAL - see row 8 | Legacy pages (e.g. /innovation, /adiance-cloud-based-thermal-camera-f/) use different branding tone, old contact numbers, and even a typo ('Ceritified') compared to the current site's polished NDAA/white-label positioning. | Brand and NAP inconsistency across old vs. current pages undermines trust (E-E-A-T) if a visitor or crawler lands on a legacy URL. | Audit and either update or retire all legacy pages identified; ensure single consistent phone numbers, certifications list, and tone site-wide. | Content/Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Brand and NAP inconsistency across old vs. current pages undermines trust (E-E-A-T) if a visitor or crawler lands on a legacy URL. | Audit and either update or retire all legacy pages identified; ensure single consistent phone numbers, certifications list, and tone site-wide. | Developer
Optimize form design and functionality | Medium | UX/UI |  | User-friendly forms with proper validation | Form testing | 4-6 hours | Medium |  | Cannot verify | Contact/enquiry forms exist (/contact, /partners) but field design and validation weren't tested in this session. |  | Manually test the contact and partner forms for validation, spam protection, and mobile usability. | QA |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Contact/enquiry forms exist (/contact, /partners) but field design and validation weren't tested in this session. | Manually test the contact and partner forms for validation, spam protection, and mobile usability. | SEO
Implement breadcrumb navigation | Low | UX/UI |  | Help users understand site hierarchy | Navigation setup | 2-3 hours | Low |  | FAIL - Not detected | No breadcrumb trail was visible in the extracted homepage or /about content. | Deep pages (country pages, product pages) may lack breadcrumb navigation, hurting both UX and BreadcrumbList schema eligibility (see row 45). | Add a visible breadcrumb component (Home > Category > Page) across all non-homepage templates. | Dev |  | ❌ REMAINING / NOT FIXED | Not built. (Note: BreadcrumbList *schema*, the invisible Google-facing version, is already live sitewide via src/seo/PageSchema.jsx — this row is specifically about a *visible* on-page breadcrumb trail for users, which is separate and does not exist yet.) | No visible 'Home > Category > Page' UI component on any template. | Build a breadcrumb UI component and add it to non-homepage templates. | Claude
Add search functionality for large sites | Low | UX/UI |  | Help users find content quickly | Search implementation | 8-12 hours | Low |  | FAIL - Not detected | No on-site search box was found in the extracted navigation. | With a blog, news, events, and dozens of product/solution pages, users have no way to search the site directly. | Add a site search (even a simple Google Programmable Search embed) to the header, especially for /blog. | Dev |  | ❌ REMAINING / NOT FIXED | Not built. | No on-site search box anywhere in the header/nav. | Add a site search (e.g. a Google Programmable Search embed, or a simple client-side search over page titles) to the header, especially for /blog. | Claude
Optimize font choices and readability | Low | UX/UI |  | Use web-safe fonts with good readability | Typography review | 2-3 hours | Low |  | Cannot verify | Not assessable from text extraction. |  | Manual visual review. | Design |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Not assessable from text extraction. | Manual visual review. | SEO
Optimize Google My Business profile | High | Local SEO |  | Complete profile with accurate information | GMB dashboard | 2-3 hours | High |  | Cannot verify | No GMB/Google Business Profile data accessible in this session. |  | Audit the Google Business Profile for Adiance Technologies directly in the GMB dashboard: categories, hours, photos, Q&A, reviews. | SEO | Google Business Profile dashboard access | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | No GMB/Google Business Profile data accessible in this session. | Audit the Google Business Profile for Adiance Technologies directly in the GMB dashboard: categories, hours, photos, Q&A, reviews. | Manual Verification
Include NAP information consistently | High | Local SEO |  | Name, Address, Phone consistent across site | NAP audit | 2-3 hours | High |  | FAIL - inconsistency found | Current site footer NAP: IN (+91) 968 777 9999 / US +1 (281) 857-2584 / Contact@adiance.com / House No. 7, Arista Eight, Corporate House, Rajpath Rangoli Rd, Bodakdev, Ahmedabad, Gujarat 380059. A legacy page (/adiance-cloud-based-thermal-camera-f/) shows a different set: +91 9510222944 / (408) 359-8800 / info@adiance.com. | Two different phone numbers and email addresses are associated with the domain in search results, which directly harms NAP consistency for local SEO and could confuse both users and Google's entity understanding. | Retire or update the legacy page's contact details to match the current footer NAP exactly; audit all directory listings (GMB, Justdial, IndiaMART, LinkedIn) for the same old number/email and correct them. | Content/SEO |  | 🔧 CAN BE FIXED BY CLAUDE | Investigated in code (2026-09-07): the specific legacy page this audit's evidence names (/adiance-cloud-based-thermal-camera-f/) already 301-redirects to /adiance-thermal-camera-f in next.config.js (from earlier work), so it should no longer be showing the old contact details live. Separately found (and fixed) a different, unrelated internal inconsistency: src/components/Topbar.jsx had its own hardcoded old phone/email (+91 9510222944 / info@adiance.com) that didn't match the site-wide NAP used in the footer and Organization schema. Fixed to match. That component is not currently imported/rendered anywhere on the live site, so it was not the actual live source of the mismatch, but is now consistent in case it's reused later. Delivered in v6.zip. | The real-world mismatch Google is seeing most likely lives OUTSIDE this codebase — in your Google Business Profile, JustDial, IndiaMART, or LinkedIn company listing still showing the old number (+91 9510222944) or email (info@adiance.com). This can't be checked or fixed from code. | Check Google Business Profile, JustDial, IndiaMART, and LinkedIn listings for the old number/email and update each to match the current footer: +91 9687779999 / sales@adiance.com (India), +1-281-857-2584 / dev@adiance.com (US). | SEO
Add location-specific keywords | Medium | Local SEO |  | Include city/region keywords naturally | Local keyword research | 3-4 hours | Medium |  | PARTIAL | geo.placename/geo.region meta tags reference Ahmedabad/Gujarat; body copy also references Ahmedabad headquarters. |  |  | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | geo.placename/geo.region meta tags reference Ahmedabad/Gujarat; body copy also references Ahmedabad headquarters. | Ask Claude to draft this content. | Claude
Create location-specific landing pages | Medium | Local SEO |  | Separate pages for different service areas | Content creation | 8-16 hours | Medium |  | N/A as retail location pages, PARTIAL as market pages | This is a B2B manufacturer, not a multi-location retailer, so classic 'service area' location pages are not applicable. However, the site does have market/region pages (/us, /global-presence, /cctv-camera-manufacturer-taiwan) which serve an equivalent purpose for international buyers. |  | Continue building region-specific pages for genuinely distinct procurement markets (e.g., UK, EU, GCC) rather than generic Indian city pages, matching the actual B2B/export business model. | SEO |  | ✅ FIXED / DONE | Confirmed the 'N/A' read is correct — classic multi-location retail landing pages don't fit a B2B export manufacturer. The site already has the right equivalent: dedicated market/region pages (/us, /global-presence, /cctv-camera-manufacturer-taiwan, and 40+ country pages). | Optional expansion, not a bug: no dedicated pages yet for a few more genuinely distinct procurement markets. | Continue building region-specific pages for real export markets (e.g. additional GCC or EU countries) rather than generic Indian city pages — matches the actual B2B model. | Claude
Implement local business schema | High | Local SEO |  | Structured data for local business info | Schema implementation | 2-3 hours | High |  | FAIL - see row 46 |  |  | See row 46 fix. | Dev |  | 🔧 CAN BE FIXED BY CLAUDE | Same fix as row 44 (idx 44 above) — app/layout.js now declares ["Organization","LocalBusiness"]. Delivered in v6.zip. | Not yet confirmed live — pending deployment, same as row 44. | Same as row 44: push v6.zip, then re-verify live. | Developer
Set up Google Analytics 4 | High | Analytics |  | Track website performance and user behavior | GA4 setup | 2-3 hours | High |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | ✅ FIXED / DONE | Verified live in GA4 (2026-09-08, property 'VMukti GA4', ID 257327900): actively collecting data — 345 users in the last 7 days, 5 active users in real time at time of check. | Nothing — GA4 is installed and tracking correctly. | No action needed. | N/A
Configure Google Search Console | High | Analytics |  | Monitor search performance and indexing | GSC setup | 1-2 hours | High |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | ✅ FIXED / DONE | Verified live in Google Search Console (2026-09-08): property verified for https://www.adiance.com/, with Performance data going back to June 2026 (4,483 total web search clicks in the reporting window). | Nothing. | No action needed. | N/A
Set up goal tracking in Analytics | Medium | Analytics |  | Track conversions and key actions | Goal configuration | 2-3 hours | Medium |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | ✅ FIXED / DONE | Verified live in GA4 Admin > Events (2026-09-08): 3 key events configured — 'contact_us_submit_success' (actively receiving data), 'blog_submit_success', and 'purchase' (not applicable, no e-commerce). | 'blog_submit_success' key event is configured but shows no stream data in the last 28 days — worth checking whether that form still fires the event. | Optional: verify the blog submission form still fires the 'blog_submit_success' GA4 event. | Developer
Implement event tracking for interactions | Medium | Analytics |  | Track button clicks, downloads, form submissions | Event setup | 3-4 hours | Medium |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | 🔧 CAN BE FIXED BY CLAUDE | Contact form submissions are tracked as a GA4 key event ('contact_us_submit_success') and actively receiving data. | GA4's own in-product recommendation (seen live 2026-09-08) suggests also tracking the 26 weekly page views on /contact as a 'generate_lead' key event for better Ads/conversion reporting. No other interaction tracking (e.g. product-page CTA clicks, brochure downloads) is confirmed set up. | Add GA4 event tracking for key CTA clicks (Request Sample, Download Datasheet, Get Quote buttons) beyond the contact form, and action GA4's own suggested 'generate_lead' event on /contact. | Claude (code) + Developer (deploy)
Create custom SEO dashboard | Low | Analytics |  | Monitor key SEO metrics in one place | Dashboard tools | 4-6 hours | Low |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Manual Verification
Set up rank tracking for keywords | Medium | Analytics |  | Monitor keyword position changes | Rank tracking tools | 2-3 hours | Medium |  | Cannot verify - requires account access | No GA4, GSC, or rank-tracking data/account access was available in this session. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Marketing/IT | GA4 + GSC account access | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot confirm tracking setup, goal configuration, or current keyword positions without direct account access. | Grant read access to GA4 property and GSC property to the SEO team, or export and share: GA4 conversion events, GSC Performance/Coverage/Core Web Vitals reports, and current rank-tracking data. | Manual Verification
Implement proper security headers | Medium | Security |  | Add CSP, HSTS, and other security headers | Security audit | 2-4 hours | Medium |  | Cannot verify | HTTP response headers were not directly inspectable in this session's fetch results. |  | Run securityheaders.com against https://www.adiance.com to check CSP, HSTS, X-Frame-Options, etc. | Dev | securityheaders.com | ✅ FIXED / DONE | Verified live via securityheaders.com (2026-09-08): www.adiance.com scores Grade A. | Nothing. | No action needed. | N/A
Add privacy policy and terms of service | Medium | Security |  | Legal compliance and trust signals | Legal review | 4-6 hours | Medium |  | PASS | Privacy Policy, Warranty Policy, and Terms of Service are all present and linked in the footer/About Us menu. |  |  | Legal/Content |  | ✅ FIXED / DONE | Already correct — Privacy Policy, Warranty Policy, and Terms of Service are all present and linked in the footer/About Us menu. | None. | No action needed — maintain as-is. | N/A
Implement GDPR compliance if applicable | High | Security |  | Cookie consent and data protection | GDPR tools | 4-8 hours | Medium |  | Cannot verify | Cookie consent banner presence/behavior not confirmed from text extraction; site markets GDPR-ready features (cloud VMS retention) but that doesn't confirm the site's own cookie compliance. |  | Verify a compliant cookie-consent mechanism is present for EU visitors given the site actively targets EU/UK buyers. | Dev/Legal |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Cookie consent banner presence/behavior not confirmed from text extraction; site markets GDPR-ready features (cloud VMS retention) but that doesn't confirm the site's own cookie compliance. | Verify a compliant cookie-consent mechanism is present for EU visitors given the site actively targets EU/UK buyers. | Developer
Add SSL certificate monitoring | Low | Security |  | Monitor SSL certificate expiration | SSL monitoring | 1 hour | Low |  | Cannot verify | Not testable in this session. |  | Set up automated SSL expiry monitoring (e.g., UptimeRobot, StatusCake). | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Not testable in this session. | Set up automated SSL expiry monitoring (e.g., UptimeRobot, StatusCake). | Developer
Implement AMP for mobile pages (if applicable) | Low | Advanced |  | Accelerated Mobile Pages for faster mobile loading | AMP validation | 16-32 hours | Low |  | N/A | This is a B2B lead-generation site, not a publisher; AMP is largely deprecated industry-wide and not relevant here. |  |  |  |  | ✅ FIXED / DONE | Confirmed not applicable to this site — This is a B2B lead-generation site, not a publisher; AMP is largely deprecated industry-wide and not relevant here. | None. | No action needed. | N/A
Set up Progressive Web App features | Low | Advanced |  | Service workers, offline functionality | PWA development | 24-40 hours | Low |  | N/A | PWA/offline functionality has no clear use case for a B2B manufacturer site. |  |  |  |  | ✅ FIXED / DONE | Confirmed not applicable to this site — PWA/offline functionality has no clear use case for a B2B manufacturer site. | None. | No action needed. | N/A
Optimize for voice search queries | Medium | Advanced |  | Target conversational, question-based keywords | Voice search research | 4-8 hours | Medium |  | PARTIAL | FAQ content style (question-based headings) is favorable for voice/AI search, but not confirmed as deliberately structured for conversational queries. |  | Expand FAQs with more natural spoken-language questions ('Is Adiance NDAA compliant?', 'Who makes non-Chinese CCTV cameras in India?'). | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | FAQ content style (question-based headings) is favorable for voice/AI search, but not confirmed as deliberately structured for conversational queries. | Expand FAQs with more natural spoken-language questions ('Is Adiance NDAA compliant?', 'Who makes non-Chinese CCTV cameras in India?'). | Claude
Implement advanced search features | Low | Advanced |  | Filters, faceted navigation for e-commerce | Development work | 16-32 hours | Low |  | N/A | No faceted/filterable product catalog exists (B2B spec-sheet style product pages), so advanced search/filtering is not a current priority. |  |  |  |  | ✅ FIXED / DONE | Confirmed not applicable to this site — No faceted/filterable product catalog exists (B2B spec-sheet style product pages), so advanced search/filtering is not a current priority. | None. | No action needed. | N/A
Create multilingual SEO strategy | Medium | Advanced |  | Hreflang tags, localized content | International SEO | 12-24 hours | Medium |  | PARTIAL | Region pages exist (/us, Taiwan, global-presence) but all in English; no hreflang or translated content confirmed. | Given active targeting of EU/GCC markets, lack of localized language content and hreflang is a real gap for those regions. | Assess whether target markets (e.g., GCC, LatAm) justify translated landing pages; at minimum add hreflang to prevent duplicate-content ambiguity between region pages. | SEO |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Given active targeting of EU/GCC markets, lack of localized language content and hreflang is a real gap for those regions. | Assess whether target markets (e.g., GCC, LatAm) justify translated landing pages; at minimum add hreflang to prevent duplicate-content ambiguity between region pages. | SEO
Schedule regular content audits | Medium | Maintenance |  | Review and update content quarterly | Audit schedule | Ongoing | Medium |  | FAIL - evidence of drift | Legacy pages (row 8/57/63) show the site has not been fully audited/cleaned after a rebrand from a more generic 'Adiance' identity to the current NDAA/white-label/ArcisAI positioning. |  | Institute a quarterly content audit specifically checking for outdated branding, old contact info, and orphaned URLs. | Content/SEO |  | ❌ REMAINING / NOT FIXED | Not started. | No recurring quarterly-audit process exists yet. | Institute a quarterly content audit checking for outdated branding, old contact info, and orphaned URLs — a process to set up, not a one-time code fix. | SEO
Update outdated information regularly | Medium | Maintenance |  | Keep statistics and information current | Content review | Ongoing | Medium |  | FAIL - see row 82 |  |  | See row 82. | Content |  | ❌ REMAINING / NOT FIXED | Not started — depends on row 82's monitoring (row 82 = idx 82, the general 404-monitoring task). | No recurring content-freshness process yet. | Same as row 80 — fold into the quarterly audit process. | SEO
Monitor and fix 404 errors | High | Maintenance |  | Regular monitoring and fixing of broken pages | 404 monitoring | Ongoing | Medium |  | Cannot verify | No 404 monitoring tool output available in this session. |  | Set up ongoing 404 monitoring via GSC Coverage report + a broken-link checker. | Dev | GSC | 👨‍💻 NEEDS DEVELOPER HELP | Verified live in Google Search Console Pages report (2026-09-08): real counts now available — 22 URLs returning 'Not found (404)', 44 'Soft 404', 8 'Server error (5xx)'. | These are real broken/error URLs on the live site right now, not yet identified by exact URL or fixed. Needs the actual URL list exported from GSC (Pages > Not found (404) / Soft 404 / Server error rows > see all examples) to fix each one (redirect, restore, or intentionally remove). | Export the exact URL lists for these 3 categories from GSC and either fix, redirect, or confirm-intentional for each. | Developer
Update XML sitemaps regularly | Medium | Maintenance |  | Ensure sitemaps reflect current site structure | Sitemap management | Monthly | Medium |  | FAIL - see row 5 |  |  | See row 5. | Dev |  | 📊 NEEDS MANUAL VERIFICATION | See row 3 (idx 3) above — same GSC sitemap-submission check. | Same as row 3. | Same as row 3. | Manual Verification
Review and update meta tags | Medium | Maintenance |  | Optimize meta tags based on performance | Meta tag audit | Quarterly | Medium |  | PARTIAL | Homepage and /about metadata are current and well-written; unclear if this is reviewed on a schedule. |  | Add meta-tag review to the quarterly content audit. | Content |  | 🔧 CAN BE FIXED BY CLAUDE | Not yet done. | Homepage and /about metadata are current and well-written; unclear if this is reviewed on a schedule. | Add meta-tag review to the quarterly content audit. | Claude
Analyze competitor SEO strategies | Medium | Research |  | Identify opportunities and best practices | Competitor analysis tools | 4-8 hours | Medium |  | Cannot verify - requires paid tool access | No Ahrefs/SEMrush/Similarweb access in this session, so real organic-visibility competitor comparisons cannot be produced responsibly (guessing rankings would be inaccurate and is against this audit's zero-assumption principle). | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | SEO | Ahrefs/SEMrush/Similarweb license | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | Manual Verification
Monitor competitor keyword rankings | Low | Research |  | Track competitor performance for target keywords | Rank tracking | Monthly | Low |  | Cannot verify - requires paid tool access | No Ahrefs/SEMrush/Similarweb access in this session, so real organic-visibility competitor comparisons cannot be produced responsibly (guessing rankings would be inaccurate and is against this audit's zero-assumption principle). | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | SEO | Ahrefs/SEMrush/Similarweb license | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | Manual Verification
Analyze competitor content gaps | Medium | Research |  | Identify content opportunities competitors are missing | Content gap tools | 4-6 hours | Medium |  | Cannot verify - requires paid tool access | No Ahrefs/SEMrush/Similarweb access in this session, so real organic-visibility competitor comparisons cannot be produced responsibly (guessing rankings would be inaccurate and is against this audit's zero-assumption principle). | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | SEO | Ahrefs/SEMrush/Similarweb license | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | Manual Verification
Study competitor backlink profiles | Low | Research |  | Understand competitor link building strategies | Backlink analysis | 3-4 hours | Low |  | Cannot verify - requires paid tool access | No Ahrefs/SEMrush/Similarweb access in this session, so real organic-visibility competitor comparisons cannot be produced responsibly (guessing rankings would be inaccurate and is against this audit's zero-assumption principle). | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | SEO | Ahrefs/SEMrush/Similarweb license | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a login/tool this session cannot access. | Cannot name real competitor keyword gaps or backlink profiles without licensed data. | Provide read access to Ahrefs/SEMrush (or export Organic Research + Content Gap reports) for identified competitor domains so a factual competitor-gap analysis can be produced. Suggested competitor set to validate: other India-based OEM/ODM CCTV manufacturers targeting NDAA compliance and non-Chinese SoC positioning (to be confirmed by actual SERP research, not assumed). | Manual Verification
Monitor Core Web Vitals regularly | High | Monitoring |  | Track LCP, FID, CLS performance monthly | PageSpeed Insights | Monthly | High |  | Cannot verify - requires GA4/GSC access | See row 67-72. |  | Same as rows 67-72: establish access, then set up recurring reporting cadence (weekly for traffic/CTR, monthly for Core Web Vitals). | Marketing | GA4 + GSC access | ✅ FIXED / DONE | Verified live via Search Console Core Web Vitals report + PageSpeed Insights (2026-09-08): Mobile field data (real visitors, Chrome UX Report) currently shows 103 'good' URLs, 0 'poor', 0 'needs improvement'. Desktop: same, 103 good, 0 poor. PageSpeed Insights Core Web Vitals Assessment for the homepage: Passed (LCP 2.2s, INP 105ms, CLS 0 — all good). | Real-user Core Web Vitals are currently passing. Lab-simulated Lighthouse Performance score for the homepage is lower (51/100 mobile) — this measures worst-case throttled conditions, not real visitors, but is still worth improving as a buffer (see row 3). | Set a recurring monthly check of this same GSC Core Web Vitals report going forward. | SEO
Track organic traffic growth | High | Monitoring |  | Monitor organic search traffic trends | Google Analytics | Weekly | High |  | Cannot verify - requires GA4/GSC access | See row 67-72. |  | Same as rows 67-72: establish access, then set up recurring reporting cadence (weekly for traffic/CTR, monthly for Core Web Vitals). | Marketing | GA4 + GSC access | ✅ FIXED / DONE | Verified live in GA4 (2026-09-08): traffic is being tracked and visible in standard reports (345 users in the last 7 days). | Nothing — tracking works. Recurring review cadence not yet formalized. | Set a recurring weekly/monthly organic-traffic review using GA4's existing Acquisition reports. | SEO
Monitor keyword ranking positions | Medium | Monitoring |  | Track target keyword performance | Rank tracking tools | Weekly | Medium |  | Cannot verify - requires GA4/GSC access | See row 67-72. |  | Same as rows 67-72: establish access, then set up recurring reporting cadence (weekly for traffic/CTR, monthly for Core Web Vitals). | Marketing | GA4 + GSC access | ✅ FIXED / DONE | Verified live in GSC Performance report (2026-09-08): real query/position data available — 4,483 total web search clicks in the current reporting window, with per-query position data in the full report. | No dedicated 3rd-party rank tracker (e.g. SEMrush position tracking) is set up — GSC's own Performance report already provides real position data at no extra cost. | Use GSC Performance > Queries (filter by position) as the ongoing rank-tracking source; a paid rank tracker is optional, not required. | SEO
Review click-through rates from SERPs | Medium | Monitoring |  | Analyze CTR performance in Search Console | Google Search Console | Weekly | Medium |  | Cannot verify - requires GA4/GSC access | See row 67-72. |  | Same as rows 67-72: establish access, then set up recurring reporting cadence (weekly for traffic/CTR, monthly for Core Web Vitals). | Marketing | GA4 + GSC access | ✅ FIXED / DONE | Verified live in GSC Performance report (2026-09-08): CTR data is available per-query and per-page in the existing report. | Nothing — data already exists, just needs a recurring review habit. | Review GSC Performance > CTR column monthly for high-impression/low-CTR pages (title/meta rewrite candidates). | SEO
Monitor bounce rate and dwell time | Medium | Monitoring |  | Track user engagement metrics | Google Analytics | Weekly | Medium |  | Cannot verify - requires GA4/GSC access | See row 67-72. |  | Same as rows 67-72: establish access, then set up recurring reporting cadence (weekly for traffic/CTR, monthly for Core Web Vitals). | Marketing | GA4 + GSC access | ✅ FIXED / DONE | Verified live in GA4 (2026-09-08): engagement metrics (engagement rate, average engagement time per session) are available in GA4's standard Engagement reports by default — GA4 replaced 'bounce rate' with 'engagement rate', which is already tracked automatically. | Nothing — GA4 default reports already cover this. | Review GA4 > Reports > Engagement monthly. | SEO
Optimize product page titles and descriptions | High | E-commerce |  | Include product benefits and key features | Product optimization | 1-2 hours/product | High |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Implement product schema markup | High | E-commerce |  | Add price, availability, review data | Schema implementation | 4-8 hours | High |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Optimize category page architecture | Medium | E-commerce |  | Clear category hierarchy and navigation | Site architecture | 8-12 hours | Medium |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Add customer reviews and ratings | High | E-commerce |  | Social proof and rich snippet opportunities | Review system | 8-16 hours | High |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Optimize product images with alt text | Medium | E-commerce |  | SEO-friendly product image optimization | Image optimization | 2-4 hours | Medium |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Implement faceted navigation properly | Medium | E-commerce |  | SEO-friendly filtering and navigation | Development work | 16-24 hours | Medium |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Create detailed product specifications | Medium | E-commerce |  | Comprehensive product information | Content creation | 1-2 hours/product | Medium |  | N/A - not a transactional e-commerce site | Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | Applying e-commerce schema/UX patterns (Product price/availability schema, faceted navigation, category architecture for browsing SKUs) would misrepresent the actual buying process. | Treat product pages as B2B spec/lead-gen pages: emphasize specifications, certifications, and a clear enquiry/quote CTA rather than e-commerce patterns. Customer reviews/ratings (item 99) is the one sub-item worth adapting as B2B case studies/testimonials, which the homepage already partially has. | Content |  | ✅ FIXED / DONE | Confirmed not applicable to this site — Adiance/ArcisAI sells via B2B enquiry (OEM/ODM partnership, MOQ from 100 units), not direct online checkout; there is no cart, pricing, or online purchase flow. | None. | No action needed. | N/A
Test website across different devices | Medium | Testing |  | Ensure consistent experience across devices | Device testing | 4-6 hours | Medium |  | Cannot verify | Not tested in this session. |  | Manual cross-device QA pass (desktop, tablet, mobile) on homepage, product pages, and forms. | QA |  | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Not tested in this session. | Manual cross-device QA pass (desktop, tablet, mobile) on homepage, product pages, and forms. | Manual Verification
Validate HTML and CSS code | Low | Testing |  | Fix markup errors that could affect SEO | W3C Validator | 2-3 hours | Low |  | Cannot verify | Not tested in this session. |  | Run W3C HTML/CSS validator on templates. | Dev | W3C Validator | 📊 NEEDS MANUAL VERIFICATION | Not yet checked — needs a crawl/scan tool run against the live site. | Not tested in this session. | Run W3C HTML/CSS validator on templates. | Manual Verification
Test site speed on various connections | Medium | Testing |  | Test performance on slow and fast connections | Speed testing tools | 2-3 hours | Medium |  | Cannot verify | Not tested in this session. |  | Test on throttled 3G/4G profiles via Chrome DevTools/PageSpeed. | Dev |  | 👨‍💻 NEEDS DEVELOPER HELP | Not yet done. | Not tested in this session. | Test on throttled 3G/4G profiles via Chrome DevTools/PageSpeed. | Developer
Conduct final SEO audit | High | Testing |  | Comprehensive review of all optimization efforts | SEO audit tools | 4-8 hours | High |  | PARTIAL - this document | This audit itself constitutes the requested final review, scoped to what is verifiable without GSC/GA4/paid-tool access. | Full closure requires the data-access items flagged throughout (GSC, GA4, Ahrefs/SEMrush, GMB, raw HTML/header inspection). | Complete the 'Data/Tool Needed' items in this sheet, then re-run this audit for full closure. | SEO |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | Full closure requires the data-access items flagged throughout (GSC, GA4, Ahrefs/SEMrush, GMB, raw HTML/header inspection). | Complete the 'Data/Tool Needed' items in this sheet, then re-run this audit for full closure. | SEO
Create SEO implementation timeline | Medium | Planning |  | Prioritize tasks and create implementation schedule | Project management | 2-4 hours | Medium |  | PASS - this document provides one | See the accompanying report's 24-hour/7-day/30-day/60-day/90-day roadmap. |  |  | SEO |  | ✅ FIXED / DONE | Already correct — See the accompanying report's 24-hour/7-day/30-day/60-day/90-day roadmap. | None. | No action needed — maintain as-is. | N/A
Document SEO processes and guidelines | Medium | Documentation |  | Create guidelines for future content and updates | Documentation tools | 4-6 hours | Medium |  | PARTIAL | This checklist itself is a documentation artifact; unclear if an internal SEO style/process guide already exists. |  | Turn this audit + the keyword-funnel decision (row 23) into a living SEO playbook for the content team. | SEO |  | 📊 NEEDS MANUAL VERIFICATION | Not yet done. | This checklist itself is a documentation artifact; unclear if an internal SEO style/process guide already exists. | Turn this audit + the keyword-funnel decision (row 23) into a living SEO playbook for the content team. | SEO
Confirm no unintended noindex tags on money pages | P0 | Indexing | P0 | FAIL - confirmed via GSC | GSC Page Indexing report (adiance.com, Aug 2026): 23 URLs excluded by 'noindex' tag. Of these, ~11 are real commercial/product/regional pages, not junk: /cctv-manufacturer-middle-east, /cctv-manufacturer-africa, /it-cctv-camera-manufacturer, /healthcare-surveillance-manufacturer, /partner, /s-series-ai-cctv-cameras, /edge-ai-based-object-face-detection-cameras/, /edge-ai-based-face-recognition-camera/, /smart-edge-ai-cloud-cctv-camera/, /customized-cctv-surveillance-cameras/, /adiance-h-265-4g-dome-ptz-camera/, /smart-anpr-lpr/, /panoramic/, /wireless-ip-cctv-camera-manufacturer-supplier/. | Likely a leftover bulk-noindex from a past rebrand/migration, never selectively reverted for pages still in active use — actively suppressing regional (Middle East, Africa, Italy) and product-line pages from Google entirely. | Remove the noindex meta tag / X-Robots-Tag header from each of the 11+ URLs listed, confirm via 'view-source' that meta robots now reads index,follow, then use GSC URL Inspection > Request Indexing on each. | Dev | FAIL - confirmed via GSC | GSC Page Indexing report (adiance.com, Aug 2026): 23 URLs excluded by 'noindex' tag. Of these, ~11 are real commercial/product/regional pages, not junk: /cctv-manufacturer-middle-east, /cctv-manufacturer-africa, /it-cctv-camera-manufacturer, /healthcare-surveillance-manufacturer, /partner, /s-series-ai-cctv-cameras, /edge-ai-based-object-face-detection-cameras/, /edge-ai-based-face-recognition-camera/, /smart-edge-ai-cloud-cctv-camera/, /customized-cctv-surveillance-cameras/, /adiance-h-265-4g-dome-ptz-camera/, /smart-anpr-lpr/, /panoramic/, /wireless-ip-cctv-camera-manufacturer-supplier/. | Likely a leftover bulk-noindex from a past rebrand/migration, never selectively reverted for pages still in active use — actively suppressing regional (Middle East, Africa, Italy) and product-line pages from Google entirely. | Remove the noindex meta tag / X-Robots-Tag header from each of the 11+ URLs listed, confirm via view-source that meta robots now reads index,follow, then use GSC URL Inspection > Request Indexing on each. | Dev | GSC URL Inspection to validate after fix | 🔧 CAN BE FIXED BY CLAUDE | Live-verified all 14 URLs this audit's evidence names, one by one, via direct fetch against www.adiance.com (2026-09-07): 5 already 301-redirect correctly to a live page from earlier work (/smart-edge-ai-cloud-cctv-camera, /smart-anpr-lpr, /panoramic, /wireless-ip-cctv-camera-manufacturer-supplier, /s-series-ai-cctv-cameras). The other 9 were genuinely 404ing with no redirect (their titles are old/renamed slugs — this is a 404-with-noindex, which is actually correct behavior, not a real 'wrongly noindexed money page' — the real bug is the missing redirect to the page that replaced each one). Added all 9: /cctv-manufacturer-middle-east, /cctv-manufacturer-africa, /healthcare-surveillance-manufacturer, /partner, /it-cctv-camera-manufacturer, /edge-ai-based-object-face-detection-cameras, /edge-ai-based-face-recognition-camera, /customized-cctv-surveillance-cameras, /adiance-h-265-4g-dome-ptz-camera — each mapped to its current equivalent page. Delivered in v6.zip. Also confirmed /seo-dashboard (mentioned in row 109) is a normal 404, not an indexed/noindexed page at all. | Not yet confirmed live — pending deployment (same as rows 44/64 above). | Push v6.zip live, then re-check each of the 9 URLs 301s correctly, then use GSC URL Inspection > Request Indexing on the destination pages. | Developer
Fix malformed URLs | P1 | Technical | P1 | FAIL - confirmed via GSC | GSC shows two malformed live URLs: https://www.adiance.com/full-solution-oem`-camera-manufacturer (contains a literal backtick character) and https://www.adiance.com/trafic-management (misspelled; a correctly-spelled /traffic-management also exists per site navigation). | Malformed/duplicate URLs waste crawl budget and look unprofessional if ever seen in a SERP or shared link. | Rename '/full-solution-oem`-camera-manufacturer' to a clean slug (e.g. /full-solution-oem-camera-manufacturer) with a 301 from the old URL; 301 redirect '/trafic-management' to '/traffic-management'. | Dev | FAIL - confirmed via GSC | GSC shows two malformed live URLs: https://www.adiance.com/full-solution-oem`-camera-manufacturer (contains a literal backtick character) and https://www.adiance.com/trafic-management (misspelled; a correctly-spelled /traffic-management also exists per site navigation). | Malformed/duplicate URLs waste crawl budget and look unprofessional if ever seen in a SERP or shared link. | Rename '/full-solution-oem`-camera-manufacturer' to a clean slug (e.g. /full-solution-oem-camera-manufacturer) with a 301 from the old URL; 301 redirect '/trafic-management' to '/traffic-management'. | Dev |  | 🔧 CAN BE FIXED BY CLAUDE | Live-verified both URLs (2026-09-07): /trafic-management already 301-redirects correctly to /traffic-management (fixed in earlier work) — nothing further needed there. /full-solution-oem`-camera-manufacturer (with the literal backtick) was genuinely still 404ing with no redirect — added both the literal- and percent-encoded-backtick forms to next.config.js, redirecting to /full-solution-oem-camera-manufacturer. Delivered in v6.zip. | The backtick-URL redirect is not yet confirmed live — pending deployment. | Push v6.zip live, then re-check the backtick URL 301s correctly. | Developer
Review public exposure of internal tooling | P0 | Security/Technical | P0 | FAIL - needs immediate review | GSC lists https://www.adiance.com/seo-dashboard as a live, crawlable, publicly accessible URL. Not opened or inspected further in this audit. | A URL named '/seo-dashboard' being publicly reachable on the production domain suggests an internal tool may be exposed without access control. | Immediately verify whether this page requires authentication; if not, either password-protect it, move it off the public domain, or block it via robots.txt + noindex + server-level access restriction (not noindex alone, since noindex does not prevent access, only indexing). | Dev/Security | FAIL - needs immediate review | GSC lists https://www.adiance.com/seo-dashboard as a live, crawlable, publicly accessible URL. Not opened or inspected further in this audit. | A URL named '/seo-dashboard' being publicly reachable on the production domain suggests an internal tool may be exposed without access control. | Immediately verify whether this page requires authentication; if not, either password-protect it, move it off the public domain, or block it via robots.txt + noindex + server-level access restriction (not noindex alone, since noindex does not prevent access, only indexing). | Dev/Security | Manual review of the live URL | ✅ FIXED / DONE | Live-verified (2026-09-07): https://www.adiance.com/seo-dashboard returns a normal 404 (page not found). There is no live, publicly-accessible internal tool at this address today — the audit's own evidence said it was 'not opened or inspected further,' and on inspection it is not actually exposed. | Google may still show this URL in Search Console from whenever it did exist (or was linked) — that's a stale-data cleanup, not a live security issue. | Optional: use GSC URL Inspection > Validate Fix / Request Removal on this URL so Google stops listing it. No code or access-control change needed — there is nothing to protect. | Manual Verification
Resolve high-volume 'Crawled - currently not indexed' bucket | P1 | Content Quality | P1 | FAIL - confirmed via GSC | 116 URLs on adiance.com fall into 'Crawled - currently not indexed' (the largest single bucket, 43% of all non-indexed URLs), including real content: /case-study/white-label-edge-ai-camera-japan, /blog/cctv-camera-manufacturer-india, /blog/adiance-vs-dahua, /blog/smart-city-surveillance-case-study-adiance, /complete-surveillance-solutions. | Google is crawling these pages but judging them not worth indexing — typically a thin-content, duplicate-content, or (most likely, given the pattern) client-side-rendering issue where the page's real content isn't visible in the initial HTML Google receives. | For a sample of these URLs (starting with the case-study and comparison blog posts, since they are strategically valuable), fetch the page with JavaScript disabled or via 'Fetch as Google' / URL Inspection > View Crawled Page > HTML tab, and confirm whether the main content renders server-side. If not, implement server-side rendering or static pre-rendering for blog/case-study templates. | Dev | FAIL - confirmed via GSC | 116 URLs on adiance.com fall into 'Crawled - currently not indexed' (the largest single bucket, 43% of all non-indexed URLs), including real content: /case-study/white-label-edge-ai-camera-japan, /blog/cctv-camera-manufacturer-india, /blog/adiance-vs-dahua, /blog/smart-city-surveillance-case-study-adiance, /complete-surveillance-solutions. | Google is crawling these pages but judging them not worth indexing — typically a thin-content, duplicate-content, or (most likely, given the pattern) client-side-rendering issue where the page's real content isn't visible in the initial HTML Google receives. | For a sample of these URLs, use URL Inspection > View Crawled Page > HTML tab to confirm whether the main content renders server-side. If not, implement server-side rendering or static pre-rendering for blog/case-study templates. | Dev | GSC URL Inspection tool, per-URL | 🔧 CAN BE FIXED BY CLAUDE | Root-caused and fixed in an earlier session (2026-08-31 to 2026-09-01): the site-wide bug was ~160 page templates using next/dynamic(..., { ssr: false }), which shipped an empty <body> (just a <script> tag) to Google on first crawl — exactly the 'client-side rendering' pattern this row's evidence predicts. Fixed by removing ssr:false everywhere it wasn't needed. Live-verified two of the five named example URLs this session (2026-09-07): /complete-surveillance-solutions and /case-study/white-label-edge-ai-camera-japan BOTH still return 0-content, no-<h1> HTML live — meaning the fix exists in code (confirmed working in this session's own rebuilt copy) but has not been deployed to production yet. | Not live yet. This is very likely the single biggest lever in this whole audit — 116 URLs (43% of all non-indexed pages) are stuck in this bucket, and the underlying fix already exists in code from 2026-09-01 (zips v1-v5), just not deployed. | Confirm the 2026-09-01 zips (v4, v5) were extracted and pushed live — see the note at the top of this sheet's summary. Then re-check /complete-surveillance-solutions and the other named URLs for real content in view-source, and request re-indexing in GSC for a sample. | Developer

## Categories Overview
Category | Total Tasks | High Priority | Medium Priority | Low Priority | Description
Technical | 10 | 6 | 3 | 1 | Core technical SEO foundation including HTTPS, speed, mobile optimization
Meta Tags | 7 | 3 | 3 | 1 | Title tags, meta descriptions, Open Graph, Twitter Cards
Headers | 4 | 2 | 2 | 0 | H1-H6 tag optimization and structure
Content | 10 | 3 | 6 | 1 | Keyword optimization, readability, internal linking
Images | 8 | 2 | 4 | 2 | Image optimization, alt text, compression, lazy loading
Schema | 7 | 1 | 5 | 1 | Structured data implementation for rich snippets
Internal Links | 7 | 3 | 3 | 1 | Internal linking strategy and optimization
UX/UI | 7 | 0 | 4 | 3 | User experience improvements and design optimization
Local SEO | 5 | 3 | 2 | 0 | Local business optimization (if applicable)
Analytics | 6 | 2 | 3 | 1 | Tracking setup and performance monitoring
Security | 4 | 1 | 3 | 0 | Security headers, SSL, privacy compliance
Advanced | 5 | 0 | 2 | 3 | Advanced features like AMP, PWA, voice search
Maintenance | 5 | 1 | 4 | 0 | Ongoing content and technical maintenance
Research | 4 | 0 | 3 | 1 | Competitive analysis and market research
Monitoring | 5 | 2 | 3 | 0 | Performance tracking and KPI monitoring
E-commerce | 7 | 3 | 4 | 0 | E-commerce specific optimizations
Testing | 4 | 1 | 2 | 1 | Quality assurance and validation
Planning | 1 | 0 | 1 | 0 | Strategic planning and timeline creation
Documentation | 1 | 0 | 1 | 0 | Process documentation and guidelines

## Priority Guide
Priority Level | Description | Timeline | Impact on Rankings | Business Impact
High Priority | Critical tasks that must be completed first | Week 1-2 | Major impact on rankings | Direct impact on traffic and conversions
Medium Priority | Important tasks that should be completed after high priority items | Week 3-6 | Moderate impact on rankings | Indirect impact on user experience and conversions
Low Priority | Nice-to-have optimizations that can be done when time permits | Month 2-3 | Minor impact on rankings | Long-term benefits and competitive advantage
Implementation Strategy:
Phase 1 (Week 1-2) | Complete all High Priority technical foundations
Phase 2 (Week 3-4) | Focus on High Priority content and meta optimizations
Phase 3 (Week 5-8) | Implement Medium Priority enhancements
Phase 4 (Month 3+) | Add Low Priority advanced features and ongoing maintenance
Expected Results Timeline:
2-4 weeks | Technical improvements visible in search console
6-8 weeks | Content optimizations begin showing ranking improvements
3-4 months | Full impact of optimization efforts visible in organic traffic
6+ months | Sustained growth and competitive advantage established

## Tools & Resources
Tool Category | Tool Name | Purpose | Cost | Website/Access
Technical SEO | Google PageSpeed Insights | Core Web Vitals and performance analysis | Free | https://pagespeed.web.dev/
Technical SEO | GTMetrix | Detailed performance analysis | Free/Paid | https://gtmetrix.com/
Technical SEO | Screaming Frog | Website crawling and technical audit | Free/Paid | https://www.screamingfrog.co.uk/
Keyword Research | Google Keyword Planner | Keyword research and search volume | Free | https://ads.google.com/home/tools/keyword-planner/
Keyword Research | SEMrush | Comprehensive SEO and keyword research | Paid | https://www.semrush.com/
Keyword Research | Ahrefs | Keyword research and backlink analysis | Paid | https://ahrefs.com/
Content Optimization | Yoast SEO | WordPress SEO optimization plugin | Free/Paid | https://yoast.com/
Content Optimization | Rank Math | WordPress SEO plugin alternative | Free/Paid | https://rankmath.com/
Content Optimization | Hemingway Editor | Content readability improvement | Free/Paid | https://hemingwayapp.com/
Analytics | Google Analytics 4 | Website traffic and user behavior analysis | Free | https://analytics.google.com/
Analytics | Google Search Console | Search performance monitoring | Free | https://search.google.com/search-console/
Schema/Structured Data | Google Rich Results Test | Test structured data implementation | Free | https://search.google.com/test/rich-results
Schema/Structured Data | Schema.org Validator | Validate schema markup | Free | https://validator.schema.org/
Image Optimization | TinyPNG | Image compression | Free/Paid | https://tinypng.com/
Image Optimization | ImageOptim | Mac image optimization tool | Free | https://imageoptim.com/
Site Monitoring | Google Mobile-Friendly Test | Test mobile compatibility | Free | https://search.google.com/test/mobile-friendly
Site Monitoring | SSL Labs SSL Test | SSL certificate validation | Free | https://www.ssllabs.com/ssltest/